## Sheet1
15th February 2021 FAVERSHAM TOWN COUNCIL-Highway Improvement Plan/Action Plan

HIGHWAY IMPROVEMENT PLAN – Stage 1				ACTION PLAN – Stage 2
NO.	Location	Problem and suggested remedy	Project	Cost Estimate	Funding Source	Action/Programme
			name			(Who/When)
1	Stonebridge Ponds/West street	Pedestrian safety	20mph		DfT via KCC	Sarah Ellcock has secured funding via the DfT's LTN fund for footway widening and other improvements at West Street. Will be scheduled for the 2021/22 financial year.
2	Athelstan Road/School Road Underpass	Shared cycle/pedestrian footpath.	LCWIP			KCC Traffic Schemes team-Audit required
3	Athelstan Road/School Road Underpass	Drop kerbs needed in School Road, may result in losing parking spaces?	LCWIP			KCC Traffic Schemes team-Audit required
4	Preston Park to St Catherines	Proposed shared cycle/pedestrian footpath. Possible dismount sign required.	LCWIP			KCC Traffic Schemes team-Audit required
5	Flood lane	Shared walking/Cycle route	LCWIP			KCC Traffic Schemes team-Audit required
6	Preston Park	Broken kerb, reported to KCC			KCC	Awaiting repair
7	A2 Canterbury Road	Drop kerbs needed along this route			KCC	Being considerd by KCC as per list below this table
8	Preston Street/Stone Street	Gate to prevent southern access	SBC		SBC	SBC Town centre improvements TBC
9	East street Gate	Better signage No Parking when gate closed, Double yellow lines etc	SBC		SBC	SBC Town centre improvements TBC
12	Bob Amor Close	Parking on pavement, causing obstructions			SBC/KCC	Cllr Perkins taking to JTB 2021
13	Hilton Close	Parking issues causing safety issues			KCC	Dec 2020 JTB Report
14	St Catherines & St Mary Church	Siting of new benches			PSG	TBC discuss with the Churches
33	Faversham Town Centre	Drop kerbs scheme	SBC		SBC	SBC Town centre improvements TBC
15	Faversham Town	Signage for areas of Bio diversity, need to be simplified. QR codes			PSG	Cllr Williams to design with Ali Corbel and create QR code links to FTC website
16	Faversham Town	Improve signage around town, include destinations/timings etc QR codes	SBC		SBC	SBC Town centre improvements Cllr Saunders to liase and assist with data,TBC
17	Forbes Road Underpass	Damage railings/wall, Quotes obtained	SBC	£3-4k	SBC ?	SBC Town centre improvements TBC
18	Town Centre	Pedestrian safety concerns, Pedestrian only Zone	SBC		SBC ?	SBC Town centre improvements TBC
19	Abbey street/Abbey Place	Improving Vehicle passing and parking			KCC/SBC	Abbey Neighbourhood Association proposal. Now with JTB
20	Whitstable Road	Flooding, run of from Rec, KCC,SBC improving the drains, work to improve part of works in The Rec			SBC	SBC completed work, KCC completed work to drain surface water faster into Cooksditch
21	Town Centre	New planters, size style best for Faversham			PSG	Committee is considering quotes and locations.
22	Faversham Town	Area mapped to show possible areas for new planting, trees etc Possibly use map as per item 10			PSG	Need to liase with Climate and Biodiversity committee.
23	Town Centre	Water/Drinking Fountain	SBC		SBC	Bottle filling station to be installed at Central car park toilets.
24	Town Centre	CCTV Areas covered, Map showing camera Range				Cllr Saunders requesting.
34	Ospringe Road B2040	Informal crossing required, near chip shop	20mph		DfT?	request an outline design from PJA
35	Cambridge road and School Road	Problems for pedestrians to cross road, due to speeding vehicles.	LCWIP		20mph committee to consider	Closing off roads to create traffic free neighbourhood. Highways Agreement, KCC
36	South Road/West street junction	HGV damage to kerb and pavement				Report on KCC fault reporting tool.
	Preston Park – Preston Avenue	install dropped kerbs			KCC	Reported by COJ and Maria, forward to Alan Blackburn
25	West street/South Road junction	Vehicles entering the western end of pedestrian zone by driving over pavement at West street/South Road junction, bollard/s		£800 - £1400	PSG?	ON HOLD pending further investigation of issue.
	Norman, Briton, Saxon, Roman, Canute, Ethelbert	Dropped kerbs required at junctions			KCC	Reported by COJ and Maria, forward to Alan Blackburn
10	12 Market Place	vehicle accesses at side of 12 Market Pl, install a bollard?				ON HOLD pending further investigation of issue.
27	West street	x 3 Bike racks with sign		£300	PSG	Bike racks fitted
28	Cross lane	Graffiti on telecoms box				BT Openreach call centre, they attend within 48 hours and clean. Adam called
29	Flood lane	Tree growing from bridge over creek, Purify building		£120.00	PSG	Done
30	Beech Close, Westbrook Stream	New bench		£1k +vat		Bench fitted
32	Rear 12 Market Place	This to be loading bay only Max 20 minutes			SBC	Done
11	Ospringe Road and Lionfield.	Bollards at either end of the alley/footpath.		£1126.40+VAT	PSG	WORKS COMPLETED

	20s Plenty Scheme
	Future LCWIP scheme
	SBC Town Centre improvements scheme
	WORKS COMPLETED
	PEDESTRIAN DROP KERB REQUIREMENTS
	10th September 2020: Adam walk with member of public in mobility scooter. Route taken South Road- Stone street-Preston Street-Market Street-Court Street-Crescent Road- Abbey Street-Church street-Abbey Place towards Standard Quay. All need drop kerb improvements.