## FULL COUNCIL
No | Date | Minute Ref | Project Summary | Partners | Budget | Progress | Costs to Date | Comments | Status
| 04.01.21 | 319 | Add signature to open letter National Education Union |  | #VALUE! |  |  |  | Not Assigned
| 04.01.21 | 320 | Millfield Play Area Improvements: support Viridor application as a third party funder | SBC | - |  | 2449.6 | Funds taken from Youth Budget | Closed
| 04.01.21 | 321 | Education in Faversham: Call on KCC to meet the need for school places for children and young people living in and around Faversham by creating placed at schools in Faversham | KCC | - |  |  |  | Not Assigned
| 01.02.21 | 334 | Dyslexia Pledge | [5 empty] | Closed
| 01.02.21 | 337 | Signing open letter to KCC about enforcement at East Kent Recyling | Oare Parish Council |  |  |  |  | Closed
| 07.12.20 | 301 | Payment of grants |  | 26000 |  | 18247 |  | Closed
[5 empty] | 10000 |  | 4998 | Taken from Allotments Budget | Closed
[5 empty] | 40000 |  | 4916 | Taken from Youth Budget | Closed
| 07.12.20 | 306 | Town Jetty proposal from Creek Navigation Co |  | - | Meeting on hold due to lockdown |  |  | Open
| 07.12.20 | 307 | Community Governance Review | SBC, parish councils | - | Letter from Electoral Services | - |  | Open
| 07.12.20 | 308 | Faversham Lakes - letter of support for the Woodland Trust | Andersons | - | Letter sent to Andersons and trees have been approved |  |  | Closed
| 07.12.20 | 309 | Cleve Hill Solar Park | Solar Cycle Way | - | Letter sent to developer asking to address issues that might prevent a cycleway being developed and make a firm commitment to working with partners to build and fund an off road cycleway between Faversham and Seasalter | - | No response received | Open

## Climate & Biodiversity
No | Date | Minute Ref | Project Summary | Partners | Budget | Progress | Costs to Date | Comments | Status
|  | Annual Action Plan | Encourage Active Transport: Encourage implementation of SBC's Walking and Cycling Plan. Review town wide electric bike and car schemes. Work wih others to ensure walking routes are identified and highlighted by better signage | Public Spaces Committee, 20's Plenty Committee |  |  |  |  | Open
| 08.03.21 |  | Biodiversity in Public Spaces: Facilitate the planting of wild flowers in grass verges, working with local groups. | KCC, SBC, Faversham in Bloom, | 500 | Purchase of wildflower seeds agreed |  | To coincide with Earth Day. Officers to hand out due to purdah | Open
| 25.01.21 |  | Living Roof Bus Shelters |  |  | 2 quotes received for The Mall and Stone Street |  |  | Open
| 08.03.21 |  |  |  |  | Agreed to accept quotes and request discount |  |  | Open
|  |  | Tree Planting | The Woodland Trust, Trees for Farms, Friends of the Earth, landowners, SBC, KCC | 500 | 1,000 trees given away in November 2020 |  |  | Closed

## Allotments
No | Date | Minute Ref | Project Summary | Partners | Budget | Progress | Costs to Date | Comments | Status

## 20's Plenty
Potential projects for enhancing 20mph (short term) and promoting walking and cycling (longer term) as at Feb-21
# | Intervention | Location / other detail |  | PJA fee | Agreed 4/2/21 | Next actions (immediate items - emboldened) | Who | Original phasing | Draft phasing
2 | Centre line removal | Various |  | 2500 | Y | PJA/KCC to propose priorities for centre-line removal to FTC (up to £5k) | PJA/JW | Phase 2 | Phase 2
3 | [5 empty] | Identify other operational interventions planned (resurfacing or re-lining). Note: Bysing Wood Road to be resurfaced in 2021 | JW | NA
4 | Enhanced gateways | General |  |  |  | Review designs following experience using planters (may alter quantities/costs to implement) | PJA/JW | NA | NA
5 |  | Bysing Wood Road |  | 1500 | Y | Detailed design for gateway near pedestrian refuge, including possible improvements to Western Link junction | PJA | Phase 1 | Phase 2
6 |  | The Mall |  | 1500 | Y | 1) Outline design for crossing point at junction with A2, to include enlarged island; 2) Determine whether to move gateway (consider parking and bus stop) | PJA PJA/JW/FTC | Phase 1 | Phase 2
7 |  | Whitstable Road |  |  |  | Defer for now. Consider in longer term need to replace with 2 gateways on Graveney Road and Love Lane. Exact locations to be confirmed, depending in part on S106 highway improvements. Consider speed limit reductions on GR and LL | FTC/KCC | Phase 1 | Phase 3/4
8 |  | Oare Road |  |  |  | No further action pending decisions about rest of Oare Road | FTC | Phase 1 | Phase 3->
9 |  | Ospringe Road |  |  |  | None for now; consider new crossing to play area | FTC | Phase 1 | Phase 3->
10 | Cross town walking route | Rec to South Road |  | 1500 | Y | 1) Review drawings 2) Provide implementation costs & schedule 3) Consider whether to implement Newton Road interventions - build outs on gatefield and Solomons Lane independently of walking route | PJA JW FTC | Phase 3 | Phase 3
11 | Healthy Streets | Possible candidates: School Road / Saxon Road Athelstan Road area St Mary’s / St John’s Other?? |  | 6200 |  | Defer for inclusion in LCWIP. Consider: 1) Develop concept in advance? 2) Community driven / public engagement on alternatives? 3) Cross town walking route separately (above)? 4) Enhancements around Kingsnorth and Athelstan roads separately? | FTC | NA | Phase 4
12 | Pedestrian crossings | General |  |  |  |  | FTC/PJA | NA | NA
13 |  | Forbes Road (Athelstan Road) |  | 500 | Y | Detailed drawings, consider including (staggered) residents parking on Forbes Road; Implement soon (Phase 2) OR in conjunction with LTN for Athelstan Road (Phase 4?) | PJA | NA | Phase 2/4
14 |  | The Mall / Forbes Road |  | 500 | Y | 1) Confirm whether crossing now acceptable. If so… 2) Develop details from existing drawing. Note: Consider impact on possible future pedestrian flow changes from changes to A251 / Mall junctions with A2 & possible LTN in Athelstan Road | JW PJA/FTC | NA | Phase 3/4
15 |  | Whitstable Road |  | 500 | Y | Consider benefit of informal crossing @ Millfield Rd, build out / raised table etc with a view to producing drawing when funds allow | PJA | NA | Phase 3/4
16 |  | Stonebridge Way / Davington Hill / Dark Hill |  | 500 | Y | Informal crossing with build out - being pursued independently of 20mph project | FTC | NA | Phase 3->
17 | Cycle Lanes | Bysing Wood Road |  |  |  | Monitor impact of centre line removal | KCC | NA | Phase 3/4
18 | [5 empty] | Consider cycleway design as part of LCWIP, particularly junctions | FTC/PJA | NA | Phase 4
19 |  | Lower Road |  |  |  | Consider cycleway along Lower Road as part of LCWIP | FTC/PJA | NA | Phase 4
20 | Other | Bramblehill road / Reedland Crescent |  | 5000 |  | Draw up design to reduce road widths - implement when funds allow | PJA | NA | Phase 3->
21 |  | Lower Road |  | 1500 | Y | Produce detailed drawings based on existing outline drawings; implement once funding available | PJA | Phase 2 | Phase 3
22 |  | Oare Road |  |  |  | Consider possible changes to Oare Road, particularly near Ham Road | PJA | Phase 2 | Phase 3
23 |  | Graveney Rd & Love Lane |  |  |  | Speed limit reductions - see above re Whitstable Rd gateway | FTC/KCC | NA | Phase 3->
24 |  | Western Link |  | NA |  | None for now - add to long list | FTC/KCC | NA | Phase 3->
|  | Total possible PJA fees |  | 21700 |  | Junction tightening - maybe low cost
|  | Proposed for PJA 4-Feb-2021 |  | 10500
Notes
Quantities and costs to remove centre lines on Whitstable, Lower, Oare and Bysing Wood roads & the Mall. £5500 - 153m of centre line to remove - hydroblast; £500 - traffic management signing; £570 - temporary road closure incl advert
Site clearance - £1100; Drainage - £700; Earthworks - £400; Pavements - £300; Kerbs/Footways/Paved areas - £7000. Total - £9500 per gateway
Moving of planters has reduced safety concerns and proposal is to move gateway near to Western Link
Planters show what is possible. Less concern from KCC about bus stop location; KCC to review as part of A251 / A2 junction changes
Gateway to move eastwards of railway bridge to Love Lane and Graveney Road, either temporarily with planters or permanently
Consider whether any intervention possible
"Make Faversham better place", easier to visit on foot; Consider local communities part-funding / maintaining community corners? Quantities for initial concept already calculated
1. Traffic and baseline study (Third party telematics data to understand vehicle flows, incl "through traffic") to support development per area, inform design (e.g modal filter placement). Make the case for concept 2. Cell boundaries 3. LTN design (incl. 1 set of revisions) and cost estimate 4. Presentation
Outline cost estimate to design and implement - £2,000 for 4 designs incl 1 rev
Resurfacing of BWR may open possiblity of new design for cycle lane.
New development at end of LR has cycleway included
Speed cushions
Consider speed reduction

## Public Spaces
15th February 2021 FAVERSHAM TOWN COUNCIL-Highway Improvement Plan/Action Plan
HIGHWAY IMPROVEMENT PLAN – Stage 1 |  |  |  | ACTION PLAN – Stage 2
NO. | Location | Problem and suggested remedy | Project | Cost Estimate | Funding Source | Action/Programme
|  |  | name |  |  | (Who/When)
1 | Stonebridge Ponds/West street | Pedestrian safety | 20mph |  | DfT via KCC | Sarah Ellcock has secured funding via the DfT's LTN fund for footway widening and other improvements at West Street. Will be scheduled for the 2021/22 financial year.
2 | Athelstan Road/School Road Underpass | Shared cycle/pedestrian footpath. | LCWIP |  |  | KCC Traffic Schemes team-Audit required
3 | Athelstan Road/School Road Underpass | Drop kerbs needed in School Road, may result in losing parking spaces? | LCWIP |  |  | KCC Traffic Schemes team-Audit required
4 | Preston Park to St Catherines | Proposed shared cycle/pedestrian footpath. Possible dismount sign required. | LCWIP |  |  | KCC Traffic Schemes team-Audit required
5 | Flood lane | Shared walking/Cycle route | LCWIP |  |  | KCC Traffic Schemes team-Audit required
6 | Preston Park | Broken kerb, reported to KCC |  |  | KCC | Awaiting repair
7 | A2 Canterbury Road | Drop kerbs needed along this route |  |  | KCC | Being considerd by KCC as per list below this table
8 | Preston Street/Stone Street | Gate to prevent southern access | SBC |  | SBC | SBC Town centre improvements TBC
9 | East street Gate | Better signage No Parking when gate closed, Double yellow lines etc | SBC |  | SBC | SBC Town centre improvements TBC
12 | Bob Amor Close | Parking on pavement, causing obstructions |  |  | SBC/KCC | Cllr Perkins taking to JTB 2021
13 | Hilton Close | Parking issues causing safety issues |  |  | KCC | Dec 2020 JTB Report
14 | St Catherines & St Mary Church | Siting of new benches |  |  | PSG | TBC discuss with the Churches
33 | Faversham Town Centre | Drop kerbs scheme | SBC |  | SBC | SBC Town centre improvements TBC
15 | Faversham Town | Signage for areas of Bio diversity, need to be simplified. QR codes |  |  | PSG | Cllr Williams to design with Ali Corbel and create QR code links to FTC website
16 | Faversham Town | Improve signage around town, include destinations/timings etc QR codes | SBC |  | SBC | SBC Town centre improvements Cllr Saunders to liase and assist with data,TBC
17 | Forbes Road Underpass | Damage railings/wall, Quotes obtained | SBC | £3-4k | SBC ? | SBC Town centre improvements TBC
18 | Town Centre | Pedestrian safety concerns, Pedestrian only Zone | SBC |  | SBC ? | SBC Town centre improvements TBC
19 | Abbey street/Abbey Place | Improving Vehicle passing and parking |  |  | KCC/SBC | Abbey Neighbourhood Association proposal. Now with JTB
20 | Whitsable Road | Flooding, run of from Rec, KCC,SBC improving the drains, work to improve part of works in The Rec |  |  | SBC | SBC completed work, KCC completed work to drain surface water faster into Cooksditch
21 | Town Centre | New planters, size style best for Faversham |  |  | PSG | Committee is considering quotes and locations.
22 | Faversham Town | Area mapped to show possible areas for new planting, trees etc Possibly use map as per item 10 |  |  | PSG | Need to liase with Climate and Biodiversity committee.
23 | Town Centre | Water/Drinking Fountain | SBC |  | SBC | Bottle filling station to be installed at Central car park toilets.
24 | Town Centre | CCTV Areas covered, Map showing camera Range |  |  |  | Cllr Saunders requesting.
34 | Ospringe Road B2040 | Informal crossing required, near chip shop | 20mph |  | DfT? | request an outline design from PJA
35 | Cambridge road and School Road | Problems for pedestrians to cross road, due to speeding vehicles. | LCWIP |  | 20mph committee to consider | Closing off roads to create traffic free neighbourhood. Highways Agreement, KCC
36 | South Road/West street junction | HGV damage to kerb and pavement |  |  |  | Report on KCC fault reporting tool.
| Preston Park – Preston Avenue | install dropped kerbs |  |  | KCC | Reported by COJ and Maria, forward to Alan Blackburn
25 | West street/South Road junction | Vehicles entering the western end of pedestrian zone by driving over pavement at West street/South Road junction, bollard/s |  | £800 - £1400 | PSG? | ON HOLD pending further investigation of issue.
| Norman, Briton, Saxon, Roman, Canute, Ethelbert | Dropped kerbs required at junctions |  |  | KCC | Reported by COJ and Maria, forward to Alan Blackburn
10 | 12 Market Place | vehicle accesses at side of 12 Market Pl, install a bollard? |  |  |  | ON HOLD pending further investigation of issue.
27 | West street | x 3 Bike racks with sign |  | 300 | PSG | Bike racks fitted
28 | Cross lane | Graffiti on telecoms box |  |  |  | BT Openreach call centre, they attend within 48 hours and clean. Adam called
29 | Flood lane | Tree growing from bridge over creek, Purify building |  | 120 | PSG | Done
30 | Beech Close, Westbrook Stream | New bench |  | £1k +vat |  | Bench fitted
32 | Rear 12 Market Place | This to be loading bay only Max 20 minutes |  |  | SBC | Done
11 | Ospringe Road and Lionfield. | Bollards at either end of the alley/footpath. |  | £1126.40+VAT | PSG | WORKS COMPLETED
20s Plenty Scheme
Future LCWIP scheme
SBC Town Centre improvements scheme
WORKS COMPLETED
PEDESTRIAN DROP KERB REQUIREMENTS
10th September 2020: Adam walk with member of public in mobility scooter. Route taken South Road- Stone street-Preston Street-Market Street-Court Street-Crescent Road- Abbey Street-Church street-Abbey Place towards Standard Quay. All need drop kerb improvements.

## Policy & Finance
No | Date | Minute Ref | Project Summary | Partners | Budget | Progress | Costs to Date | Comments | Status
|  | Annual Action Plan 2020-21 | Engaging with all youth, particularly those harder to reach: (a) Identify potential partners (b) Develop a youth engagement plan |  |  |  |  | Deletegated to the Youth Working Group | Open
|  | Annual Action Plan 2020-21 | Diversity and Equality: (a) Support a Fairer Faversham by making equality and diversity issues a priority at all levels of the Council as a key part of the decision making process (b) Ensure that facilities and events are accessible and welcoming to all communities (c) Foster greater community cohesion by creating a town where difference and diversity is understood, celebrated and valued (d) Seek to implement, where possible, recommendations made by the Electoral Commission or other independent bodies aimed at reducing barriers to standing for election to this council |  |  |  |  | Delegated to the Equality & Diversity Working Group | Open

## Heritage WG
No | Date | Minute Ref | Project Summary | Partners | Budget | Progress | Costs to Date | Comments | Status
|  |  | Doddington Library |  |  | Shelving all installed and books in place |  | Official opening awaited | Closed
|  |  | Shand Fire Pump |  |  | Loan agreement signed. Moved to Shepherd Neame |  |  | Closed

## The Guildhall
GUILDHALL WORKS REQUIRING FUNDING MARCH 2021
NEW HEATING | 3850 |  | Completed
INTERIOR WINDOW REPAIRS | 4464 |  | Completed
INTERIOR WINDOW DECORATING | 2500 |  | Completed
INTERIOR WOOD DECORATING BOTH ROOMS | 3000 |  | QUOTE
INTERIOR WALLS CEILINGS(including kitchen/stairwell) | 5000 |  | QUOTE
EXTERIOR DECORATING | 10000 |  | QUOTE
EXTERIOR WINDOW REPAIR | 10000 |  | QUOTE
EXTERIOR SCAFFOLDING | 12500 |  | QUOTE
NEW ROOF GUILDHALL | 40000 |  | ESTIMATE
SURVEY ROOF BEAMS BEFORE NEW ROOF | 4760 |  | Completed
x3 FIRE DOORS GUILDHALL, MEET FIRE REGULATIONS | 2500 |  | QUOTE
BELL TOWER LEAK | 1540 |  | Completed
WOODEN FLOOR REPAIRS/ SANDED/WAXED | 3000 |  | ESTIMATE
Have supplied 3 quotes, one quote all is included, the other two I will need to arrange the wood working also the scaffolding and materials.
PRIORTY
| HIGH | MEDIUM | LOW
February - March 2021 | COMPLETED

## Youth WG
No | Date | Minute Ref | Project Summary | Partners | Budget | Progress | Costs to Date | Comments | Status

## Town Marketing WG
No | Date | Minute Ref | Project Summary | Partners | Budget | Progress | Costs to Date | Comments | Status
|  |  | Marketing Plan actions |  |  | TMG Meeting – 2nd March, new Town Trail “West to East Trail” update; AONB Linking Coastal Paths to Downs Project update (TMG Councillors agreed to re-brand ‘food trails’ to have a countryside message – Countryside Trails, for potential funding from AONB linking as above – 5k potential funding on a 69/31% basis (31% match funded by FTC). Ongoing discussions to establish workstream criteria and timeframe. |  |  | Open
[6 empty] | Events 2021/22 – TMG recommends not organising any main events for 2021 but to concentrate on marketing and support of other events being organised by groups, business, attractions, etc. To put resources and efforts into 2022 events, i.e. FOT & June Jubilee. |  |  | Open
[6 empty] | TMG recommends a Civic Memorial service try to be arranged towards the end of 2021 if possible – discuss with LB & AB to organise Civic service. |  |  | Open
[6 empty] | Crab Island sign - CW chasing Graeme Tuff at SBC chased up on progress. New sign in Oare Road reported in disrepair by Adam – currently trying to source the base artwork for the Crab Island signage (SBC in process of replacing the sign with new artwork) so that we can create artwork along the same lines for Oare Road. |  |  | Open
[6 empty] | Key marketing messages – extend the season, re-connect with nature, a great place to live is a great place to visit, respect-protect-enjoy. Questions from visitors “what can I do, where can I do it”. |  |  | Open
[6 empty] | Itineraries - Explore putting together for trips, further calls for content from attractions in preparation for coming out of lockdown. Travel abroad will be avoided, UK domestic tourism & staycations moving forward. |  |  | Open
|  |  | Footfall counts and empty car park spaces counts |  |  | Plan footfall counts before 12th April on a market & non market day. |  |  | Open
|  |  | Contact with local tourism attractions, organisations, groups, etc. |  |  | Huckleberry Woods – phone call & email regarding You Tube channel, submitting video for VF content & social posts. |  |  | Closed
[6 empty] | DMG (Destination Marketing Group) – set up meeting for late March/early April. |  |  | Closed
[6 empty] | Brogdale Collections – lottery raffle prize, SM posts & training feedback to SBC. Discussions re their Easter event plans & plans for rest of year. Low key following Gov. guidance as released. |  |  | Closed
[6 empty] | Visit Kent – launch of Art Home project; passed to relevant self catering accommodation contacts to get involved. Industry update webinar on 23.3.21, |  |  | Closed
[6 empty] | Sandhurst Forge Farm & Belmont House – calls re website entries. 3.3.21 phone call re AONB contact for inclusion on linking Coastal Paths to Kent Downs; AONB looking for ‘craft’ businesses along their new routes to link with. |  |  | Closed
[6 empty] | Black Oast Guest House – 4.3.21 phone call regarding re-opening and accommodation listing on VF; details and images to follow to add to website and FB post. |  |  | Closed
|  |  | Social media channels & Visit Faversham website |  |  | Visit Faversham Facebook – 5,354 followers, last 28 days post reach of 2,332; post engagement 500. 15 posts – most popular post on 7.2.21 “Brogdale’s Grow a Pip” 907 reach. |  |  | Open
[6 empty] | Visit Faversham Instagram – 2,097 followers |  |  | Open
[6 empty] | Visit Faversham Website – January 2021 stats: Visit Faversham page on Visit Swale most visited page. Visit Kent site (features Visit Faversham) January over 400 page visits. |  |  | Open
|  |  | Marketing literature, signage |  |  | Faversham History Boards – further 2 copy supplied (Anthony Millet): “Court Street – captive monarchs & monastic breweries” & “Welcome to Faversham – port & market town of Kings” |  |  | Open
[6 empty] | Food Trails leaflets x 8 A4 6pp – update content, replace rear page with Healthier, Safer, Cleaner message & include town walk from West Faversham Community centre to Love Lane – currently being worked on as below. Potential involvement with Fav. Soc TBC. Item 11 below refers re linking with Kent AONB – linking coast to downs project. |  |  | Open
[6 empty] | NEW Faversham Town Walk – received copy from Antony Millet, time spent reducing the copy and brief for illustrators to quote for artwork for map & buildings to be illustrated as other two town trails. CW will artwork leaflet & securing two quotes for artwork – quote accepted for £484 – illustrations deadline 25.3.21. Have map already & some illustrations, layout working on. |  |  | Open
|  |  | Newsletter |  |  | Summer 2021 edition – booked delivery for w/c 28.6.21. RM to include new postcode sectors for new builds now occupied. |  |  | Open
|  |  | SBC joints initiatives & SBC Visitor Economy Framework actions/liaison |  |  | SAG Vicky Hadfield – 17.2.21 phone discussion re SAG events criteria for outdoor events; advised there will be additional step to go through for events to ensure Covid Resilience at events – headed by Julie Oats, Environmental Health Officer at SBC. Pilot events to be run by Gov. results of which will inform future SM measures & interventions to ensure covid resilience. |  |  | Open
[6 empty] | Martin Goodhew – weekly calls re VF website & walks update. |  |  | Open
[6 empty] | Discussions to create a new build resident information pack to showcase the area for prospective buyers. Work been done on this last year, postcard campaign, etc. by the group – Liz (Shoreway Marketing) to provide CW with previous consultations, contacts, etc. for CW to further investigate and propose joint literature initiative with group members & beyond. |  |  | Open
|  |  | Events |  |  | FOT 2021 (Festival of Transport) – cancellation of 2021 event emails sent as appropriate, FB post made & key contacts advised. Committee advised – proposed date for 2022 14th-15th May. |  |  | Open
[6 empty] | Queen’s Platinum Jubilee – Thursday 2nd – Friday 3rd June 2022 – plan a Prom and other activities. Railway Swing Band booked for Friday 3rd June 2022 Proms in Market Place. |  |  | Open
[6 empty] | Contacted Market Ass. To see if Friday & Saturday market be themed ‘Through the Decades’ for Faversham. Contacted Faversham Society (Antony Millet/Harold Goodwin) to put on two week exhibition ‘Faversham Through the Ages/Decades’ – awaiting feedback/ideas from both. Meeting Market Ass. In New Year to flesh out further. |  |  | Open
[6 empty] | Civic Service on Sunday 5th June 2022 – LB & AB to assist. |  |  | Open
|  |  | Youth & Local Education Providers |  |  | Fun Days in school holidays – advised BW on Event Management Plan for such an event proposed to run on open space in each Ward and Fav. Rec.; requirement to go via SAG with 12 weeks’ notice. Advised on SAG current status regarding outside event approval. EMP required even if event is on land not owned by FTC if Brook to be event organiser – suggested she contact Ben Simons at SBC (Rec Manager) to see if SBC doing anything. |  |  | Closed
|  |  | Media exposure & advertising |  |  | Faversham Life – article Floragy Skincare - Faversham Life |  |  | Closed
[6 empty] | Inside Kent – April feature ‘48 Hours in Faversham’ will be published in print & on line. Design & supply quarter page advert to support the feature article. |  |  | Open
|  |  | Travel trade & regional tourist associations/boards, transport & other actions |  |  | Kent Downs – Sally Evans, Linking Coast to Downs Project – potential funding of £5k, match funded 69/31 (31% FTC contribution) to change emphasis of 8 trails to ‘countryside’ message, green tourism, linking coastal paths to Kent Downs as comments above under TMG update. CW to meet Sally (virtual) 17.3.21 to flesh out work programme and funding from AONB. |  |  | Closed
|  |  | Colleague Support |  |  | Faversham & District Community Lottery – good causes sign up support to LB; liaison with Gatherwell regarding website & FB presence. Follow up emails to good causes signed up. Design, set & supply adverts for KM Group, on line adverts, radio advert & adverts for The Net starting 9.3.21. Banners created, ordered and put up by Adam. Editorials sent to press. FB posts created, static & video clips. Working Group meeting 2.3.21, 7.30pm Zoom. Next meeting 6.4.21. |  |  | Open
[6 empty] | Keep Faversham Buzzing/Seed Giveaway – logo design. |  |  | Open
[6 empty] | FCLT - (Faversham Community Land Trust) logo design. |  |  | Open