## TOWN_HIP
27th May 2021 FAVERSHAM TOWN COUNCIL-Town wide desirable improvements

NO.	Location	Problem and suggested remedy	Funding	Action/Programme
				(Who/When)
6	Preston Park	Broken kerb, reported to KCC	KCC	Completed
7	A2 Canterbury Road	Drop kerbs needed along this route	KCC	Being considerd by KCC as per list below this table
14	St Catherines & St Mary Church	Siting of new benches	PSG	TBC discuss with the Churches
15	Faversham Town	Signage for areas of Bio diversity, need to be simplified. QR codes	PSG	Cllr Williams to design with Ali Corbel and create QR code links to FTC website
16	Faversham Town	Improve signage around town, include destinations/timings etc QR codes		SBC Town centre improvements Cllr Saunders to liase and assist with data,TBC
18	Town Centre	Pedestrian safety concerns, Pedestrian only Zone		SBC Town centre improvements TBC
20	Whitstable Road	Flooding, run of from Rec, KCC,SBC improving the drains, work to improve part of works in The Rec	SBC	SBC completed work, KCC completed work to drain surface water faster into Cooksditch
21	Town Centre	New planters, size style best for Faversham	PSG	See today agenda
22	Faversham Town	Area mapped to show possible areas for new planting, trees etc Possibly use map as per item 10	PSG	In progress
23	Town Centre	Water bottle filling station required
24	Town Centre	CCTV Areas covered, Map showing camera Range		Cllr Saunders requesting.
35	Cambridge road and School Road	Problems for pedestrians to cross road, due to speeding vehicles.	KCC	Closing off roads to create traffic free neighbourhood.
36	South Road/West street junction	HGV damage to kerb and pavement		Report on KCC fault reporting tool.
	Preston Park – Preston Avenue	install dropped kerbs	KCC
25	West street/South Road junction	Vehicles entering the western end of pedestrian zone by driving over pavement at West street/South Road junction, bollard/s	PSG?	ON HOLD pending further investigation of issue.
57	Norman, Briton, Saxon, Roman, Canute, Ethelbert	Dropped kerbs required at junctions	KCC	Reported by COJ and Maria, forward to Alan Blackburn
10	12 Market Place	vehicle accesses at side of 12 Market Pl, install a bollard?		ON HOLD pending further investigation of issue.
27	West street	x 3 Bike racks with sign	PSG	Bike racks fitted
28	Cross lane	Graffiti on telecoms box		BT Openreach call centre, they attend within 48 hours and clean. Adam called
29	Flood lane	Tree growing from bridge over creek, Purify building	PSG	Done
30	Beech Close, Westbrook Stream	New bench		Bench fitted
11	Ospringe Road and Lionfield.	Bollards at either end of the alley/footpath.	PSG	WORKS COMPLETED
	WORKS COMPLETED
	PEDESTRIAN DROP KERB REQUIREMENTS
	10th September 2020: Adam walk with member of public in mobility scooter. Route taken South Road- Stone street-Preston Street-Market Street-Court Street-Crescent Road- Abbey Street-Church street-Abbey Place towards Standard Quay. All need drop kerb improvements.

## KCC_HIP
Faversham Town Council – Highway Improvement Plan/Action Plan

HIGHWAY IMPROVEMENT PLAN - Stage 1			ACTION PLAN- Stage 2
Priority	Location	Problem and suggested remedy	Cost estimate	Funding Source	Action/Programme (Who/When)
1	Stonebridge Ponds/West street	Pedestrian safety			With Sarah Ellcock
2	Ospringe Road B2040	Pedestrian safety, informal crossing required to link King George V playing fields with Lionfield.			With Sarah Ellcock
3	North Lane	Pedestrian safety, informal crossing required to link town centre to the North Preston estate via Partridge Lane.
4	Athelstan Road/School Road Underpass	Shared cycle/pedestrian footpath.			KCC Traffic Schemes team-Audit required, more info required to be featured on HIP
5	Preston Park to St Catherines	Proposed shared cycle/pedestrian footpath. Possible dismount sign required.			KCC Traffic Schemes team-Audit required, more info required to be featured on HIP
6	Flood lane	Shared walking/Cycle route			KCC Traffic Schemes team-Audit required, more info required to be featured on HIP
7	Bob Amor Close	Parking on pavement, causing obstructions			Approved at March Swale JTB
8	Hilton Close	Parking issues causing safety issues			Approved at March Swale JTB
9	Faversham Town Centre	Drop kerbs scheme		KCC/SBC	Alan Blackburn KCC is scheduling those agreed with Dean Radmore SBC
10	Abbey street/Abbey Place	Improving Vehicle passing and parking			Approved at March Swale JTB
11	Preston Park – Preston Avenue	install dropped kerbs		KCC