## Sheet1
Faversham Town Council – KCC Highway Improvement Plan/Action Plan

HIGHWAY IMPROVEMENT PLAN - Stage 1			ACTION PLAN- Stage 2
Priority	Location	Problem and suggested remedy	Cost estimate	Funding Source	Action/Programme (Who/When)
1	Love Lane and Ashford Rd	Review of speeds with aim to reduced speed limit to 30mph			Following a speed survey a reduction in the speed limit has at this time been REFUSED by KCC highways
2	Ashford Road	Review of speeds with aim to reduced speed limit to 30mph			Following a speed survey a reduction in the speed limit has been AGREED by KCC highways
3	Ospringe Street	Speeding traffic action part 1; Install new white gates including village name plate in both directions 1 @ the track entrance that runs to the rear of Ospringe Place and 1 @ the farm entrance side of No.70 , refreshing CW markings (including dragons teeth). Remove existing traffic signals warning sign on downhill stretch on approach to Ospringe Road and replace with staggered junction warming sign and road narrows. Existing signs in good location but posts and signs are old and need replacing. To pair this with a SLOW marking in the CW. Additional road narrows warning sign to be installed alongside a SLOW road marking in the vicinity of No.44 at the wider FW section.			Discussed with Sarah Ellcock on a site visit to Ospringe on Thursday 29th April 2021, Sarah Ellcock is preparing a set of potential measures.
4	Ospringe Road B2040	Pedestrian safety, informal crossing required to link King George V playing fields with Lion Field.			Reported via KCC member that Sarah Ellcock plans to progress this scheme
5	North Lane	Pedestrian safety, informal crossing required to link town centre to the North Preston estate via Partridge Lane.
6	Ospringe Street	Speeding Traffic action part 2, Traffic approaching from both east and west, converge on the narrowest and lowest section of Ospringe Street, where there are three junctions and a narrow bend in Ospringe Street. Solution would be to create a 20mph zone on the section of Ospringe Street between “Grove Place” and “Ospringe Road” and south on “Water Lane” to “Mutton Lane”			Discussed with Sarah Ellcock on a site visit to Ospringe on Thursday 29th April 2021
7	Faversham Town Centre	Drop kerbs scheme		KCC/SBC	Alan Blackburn KCC is scheduling those agreed with Dean Radmore SBC
8	Athelstan Road/School Road Underpass	Shared cycle/pedestrian footpath.			KCC Traffic Schemes team-Audit required, more info required to be featured on HIP
9	Preston Park to St Catherines	Proposed shared cycle/pedestrian footpath. Possible dismount sign required.			KCC Traffic Schemes team-Audit required, more info required to be featured on HIP
10	Flood lane	Shared walking/Cycle route			KCC Traffic Schemes team-Audit required, more info required to be featured on HIP
	Preston Park – Preston Avenue	install dropped kerbs		KCC	Scheduled ???
	Stonebridge Ponds/West street	Pedestrian safety	£40k	existing budget	Scheduled for this financial year