## TOWN_HIP
25th November 2021 FAVERSHAM TOWN COUNCIL, Public Spaces Working Group – Non Highways desirable improvements

NO.	Location	Problem and suggested remedy	Funding	Action/Programme
				(Who/When)
	St Catherines & St Mary Church	Siting of new benches	PSG	TBC discuss with the Churches
	Faversham Town	Signage for areas of Bio diversity, need to be simplified. QR codes	PSG	Cllr Williams to design with Ali Corbel and create QR code links to FTC website
	Faversham Town	Area mapped to show possible areas for new planting, trees etc Possibly use map as per item 10	PSG	In progress
	Town Centre	Water bottle filling station required	SBC	SBC will install on toilet block, on SBC's TC improvement plan
	Town Centre	CCTV Areas covered, Map showing camera Range		Cllr Saunders requesting.
	West street/South Road junction	Vehicles entering the western end of pedestrian zone by driving over pavement at West street/South Road junction, bollard/s	PSG?	ON HOLD pending further investigation of issue.
	Norman, Briton, Saxon, Roman, Canute, Ethelbert	Dropped kerbs required at junctions, transfer to HIP?	KCC	Reported by COJ and Maria, forward to Alan Blackburn
	12 Market Place	vehicle accesses at side of 12 Market Pl, install a bollard?		ON HOLD pending further investigation of issue.
	Market Place	electrical power for the Market – why, feasible, funding?	SBC ?	SBC investigating and on SBC's TC improvement plan