## Sheet1
Committee / Working Group | Partners | Action Plan Item | Project Summary | Budget (Reserves) | Grants Received | Cost to Date | Progress
20's Plenty | KCC | Deliver a town-wide 20mph scheme | 20mph town-wide scheme. Consultants engaged: PJA and Adrian Berendt | 60656 |  | 13450
Awaiting consultation results for Experimental Traffic Order from KCC
Climate & Biodiversity |  | Encourage biodiversity in areas of local authority ownership | Living roof bus shelters x 2 | 30000 | 8000 | 29851
|  | Work with Faversham residents to increase biodiversity in their back gardens | Seedball giveaway |  |  | 500
|  |  | 1000 trees for Tree Week giveaway Nov/Dec 21 |  |  | 1568
|  | Promote climate emergency awareness through activities and events | Community gardening |  | 200 | 75
|  |  | Pesticide Free Town Action Plan |  |  | 0
Public Spaces |  |  | Serpentine bench refurbishment x 3 | 10000 |  | 900
Highways Improvement Plan
|  |  | Additional Planters |  |  | 3300
Heritage |  | Enhance the cultural offer by developing a permanent exhibition of the town’s Magna Carta | Faversham Charters & Magna Carta | 50000 | 56000
|  |  | Charter cases |  |  | 29800
Darius Wilson
Website
|  | Encourage community creativity and cohesion by enabling local groups to meet or exhibit for free in the Guildhall and 12 Market Place | Lease to be signed with The Faversham Society, formation of The Hatch, community exhibition space |  |  | 1600
Policy & Resources |  | Provide grants for local community events and groups | Grant applications received and considered | 34000 |  | 34000
Lottery |  | Increase income for community groups through the Faversham and District Community Lottery | Faversham & District Lottery | 5000
Neighbourhood Plan |  | Neighbourhood plan
|  | Continue to develop a neighbourhood plan |  | 50142 | 8925 | 3120
Carry out extensive consultation through community engagement
Present a neighbourhood plan which will be successful at referendum
Ensuring sport and physical activity is included in the developing neighbourhood plan
Ensure truly affordable housing is included in the developing neighbourhood plan
Improve cycling and walking
LCWIP | SBC | Deliver a Local Cycling and Walking Infrastructure Plan (LCWIP) | LCWIP. Consultants engaged: PJA and Adrian Berendt |  | 30000 | 17840
| SBC | Enhance walking routes with signage to aid connectivity | SwaleEastern Area Committee: Town to Parish Cycling |  | 12500
|  | Continue to encourage cycling and walking through community engagement and events | Cycle Fest
Youth |  | Engaging with all youth, particularly those who are harder to reach
|  | Employ a youth worker |  | 40000
Identify potential partnerships
Develop a youth engagement plan
|  | Youth Events | Youth Climate Panel exhibition 25th-30th October |  |  | 35
Silent disco Easter (rescheduled from 2020)
Town Marketing | SBC |  | Call for Ideas | 0 | 25000
| SBC |  | Back to the High Street Fund - entertainment | 0 | 2000
|  |  | Fiver Fest | 0
|  |  | Sponsorship |  | 800
|  |  | Participants 28 @ £10 |  | 280
Equality and Diversity |  | Diversity and equality
|  | Support a fairer Faversham by making equality and diversity issues a priority at all levels of the Council as a key part of the decision-making process | Faversham Disability Forum formed | 0 |  | 0
Ensure that facilities and events are accessible and welcoming to all communities
Foster greater community cohesion by creating a town where difference and diversity is understood, celebrated and valued
Seek to implement, where possible, recommendations made by the Electoral Commission or other independent bodies aimed at reducing barriers to standing for election to this council
Sports Council
|  | Identify local groups and provide a networking hub | Work being undertaken by SBC
Develop Active Faversham, encouraging the community through events and activities
Lobby both public and private bodies to gain the best for Faversham, within whose responsibility lies the following
Creek |  | An opening Creek bridge | Letter sent to SoS | 7500
|  | Supporting the regeneration of the Creek for maritime activities for work and pleasure | Front Brents Jetty refurbished, health and safety works to be carried out including electrics and ladders | 5000
Policy & Resources |  | Better engagement with Kent Police, British Transport Police and Swale Borough Council, around the occurrences and perception of anti-social behaviour | Crime research proposal |  | 9000
Develop ways to assist the homeless in Faversham
|  | Support the Faversham Community Land Trust | Free design services provided for newsletter | 0 |  | 0
Community Development Officer |  | Coordinating volunteer projects that enable the Council to fulfil its ambitions, including the climate and biodiversity emergency and youth.
|  |  | Halloween trail (25th-31st October) | 0 |  | 0
|  |  | Commuity network meeting scheduled for November | 0 |  | 0
|  |  | Christmas Mayoral community natter | 0
|  |  | Christmas trail | 650 |  | 80
|  |  | New Year New Me personal advice, mental health etc | 0
|  | Manage wedding bookings and marketing | Wedding Fair (19th-20th November) | 0 |  | 0
[5 empty] | 152705 | 136119
Cancelled
Overdue no longer assigned
Unassigned, not started, check progress
Resuming, in progress, assigned
Completed